## Project Timeline
Phase / Task | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10
Planning & Requirements
Requirements Gathering | bar: M1 to M2
System & Workflow Planning | bar: M1 to M2
Database Schema Design | bar: M2 to M3
UI/UX Design
Wireframes & User Flows | bar: M1 to M3
Visual Design System | bar: M2 to M4
High-Fidelity Designs (all roles) | bar: M3 to M8
Design Iteration & Refinement | bar: M4 to M9
Development
Authentication & Core Layout | bar: M4 to M5
Feed & Posts | bar: M5 to M6
Messaging (Real-Time) | bar: M6 to M7
Communities & Notifications | bar: M7 to M8
Pages, Events & Subscriptions | bar: M8 to M9
Testing & Delivery
Testing During Development | bar: M4 to M9
Final Testing & Bug Fixing | bar: M9 to M10
Documentation & Reporting
Final Presentation Preparation | bar: M9 to M10